## Bug_3
Category | Label | Value
Bug overview | ID number | 3 | Fixed
| Reporter | Mykhailo Loshch
| Summary | Clicking on the «Create a new board» button doesn't work on the SideBar.
Environment | Deviсe | PC
| Operating system | Windows 11 Pro 22H2 22621.1848 X64
| Browser | Google Chrome Version114.0.5735.134 (Oficial Build), (64 bit)
Bug details | Preconditions | The Web App is opened in Browser
The user is logged in.
| Steps to reproduce | Click on the «Create a new board» button on the SideBar.
| Actual result | On clicking the «Create a new board» button on the SideBar nothing happens, it doesn't work
| Expected result | On clicking the «Create a new board» button on the SideBar the «Create a new board» PopUp is opened
| Attachments | https://drive.google.com/file/d/1Wqb18lEoT2TyWk2Xk9e2-v1zm8CE-3ld/view?usp=drive_link
Bug tracking | Severity | Critical
| Priority | High
Notes | Notes | "The "Create a new board" button on the SideBar is not working.

## Bug_5
Category | Label | Value
Bug overview | ID number | 5 | Fixed
| Reporter | Mykhailo Loshch
| Summary | On clicking the «Create a new board» button on the SideBar the background on the «Create a new board» PopUp is already selected
Environment | Deviсe | PC
| Operating system | Windows 11 Pro 22H2 22621.1848 X64
| Browser | Google Chrome Version114.0.5735.134 (Oficial Build), (64 bit)
Bug details | Preconditions | The Web App is opened in Browser
The user is logged in.
| Steps to reproduce | Click on the «Create a new board» button on the SideBar.
| Actual result | On clicking the «Create a new board» button on the SideBar the background on the «Create a new board» PopUp is already selected
| Expected result | On clicking the «Create a new board» button on the SideBar the «no background» option on the «Create a new board» PopUp is selected by default
| Attachments | https://drive.google.com/file/d/1n3LHZGFXkRAkpDQHJyuIiSx_07-zoWIb/view?usp=sharing
Bug tracking | Severity | Minor
| Priority | Low
Notes | Notes

## Bug_6
Category | Label | Value
Bug overview | ID number | 6 | Fixed
| Reporter | Mykhailo Loshch
| Summary | Choosing a white or violet theme and filling in the «Email» field in the «Need Help» PopUp, the text is not visible
Environment | Deviсe | PC
| Operating system | Windows 11 Pro 22H2 22621.1848 X64
| Browser | Google Chrome Version114.0.5735.134 (Oficial Build), (64 bit)
Bug details | Preconditions | The Web App is opened in Browser
The user is logged in.
| Steps to reproduce | Choose a white or violet theme by clicking the «Theme» drop-down menu in the header
Click on the «Need Help» link on the SideBar
Enter any characters to the Email field In the «Need Help» PopUp
| Actual result | The characters entered to the «Email» field are not visible
| Expected result | The characters entered to the «Email» field are visible
| Attachments | https://drive.google.com/file/d/1wj9p7-l-M7NY-_Gv9ZWvxkNlZZU0GFXo/view?usp=sharing
Bug tracking | Severity | Minor
| Priority | Low
Notes | Notes | The white color of the text is'nt visible on a white background

## Bug_7
Category | Label | Value
Bug overview | ID number | 7 | Fixed
| Reporter | Mykhailo Loshch
| Summary | When you select a white or purple theme and fill in the Question field in the Need Help modal, no text is visible.
Environment | Deviсe | PC
| Operating system | Windows 11 Pro 22H2 22621.1848 X64
| Browser | Google Chrome Version114.0.5735.134 (Oficial Build), (64 bit)
Bug details | Preconditions | The Web App is opened in Browser
The user is logged in.
| Steps to reproduce | Choose a white or purple theme by clicking on the "Theme" drop-down menu in the header.
Click on the "Need Help" link on the sidebar.
In the "Need Help" modal window, enter any characters in the "Question" field.
| Actual result | Characters are entered but not visible.
| Expected result | Characters are entered and visible.
| Attachments | https://drive.google.com/file/d/1IIuHNQEPpBlPLbSfENFXFEBoQBB98_v5/view?usp=sharing
Bug tracking | Severity | Minor
| Priority | Low
Notes | Notes | The colour of the text is white on a white background and is not visible.

## Bug_8
Category | Label | Value
Bug overview | ID number | 8 | Fixed
| Reporter | Mykhailo Loshch
| Summary | The "Need Help" modal window disappears if you select the entered data in the "email" field with the left mouse button from right to left.
Environment | Deviсe | PC
| Operating system | Windows 11 Pro 22H2 22621.1848 X64
| Browser | Google Chrome Version114.0.5735.134 (Oficial Build), (64 bit)
Bug details | Preconditions | The Web App is opened in Browser
The user is logged in.
| Steps to reproduce | Click on the "Need Help" link on the sidebar.
In the "Need Help" modal window, enter any characters in the Email field.
Use the left mouse button to highlight the characters entered in the Email field from right to left until the "Need Help" modal window disappears
| Actual result | By selecting the characters entered in the Email field with the left mouse button several times from right to left, the "Need Help" modal window disappears
| Expected result | The characters entered in the Email field are highlighted with the left mouse button from right to left, and the "Need Help" modal window does not disappear
| Attachments | https://drive.google.com/file/d/1A69sU93NTIIHuKfyje3CYLUplJ5iGnoa/view?usp=sharing
Bug tracking | Severity | Minor
| Priority | Medium
Notes | Notes | The modal window disappears only when you select from right to left.

## Bug_9
Category | Label | Value
Bug overview | ID number | 9 | Fixed
| Reporter | Mykhailo Loshch
| Summary | The "Need Help" modal window disappears if you select the entered data in the "Question" field with the left mouse button from right to left
Environment | Deviсe | PC
| Operating system | Windows 11 Pro 22H2 22621.1848 X64
| Browser | Google Chrome Version114.0.5735.134 (Oficial Build), (64 bit)
Bug details | Preconditions | The Web App is opened in Browser
The user is logged in.
| Steps to reproduce | Click on the "Need Help" link on the sidebar.
In the "Need Help" modal window, enter any characters in the Question field. .
Highlight the characters entered in the Question field with the left mouse button from right to left until the "Need Help" modal window disappears
| Actual result | By selecting the characters entered in the Question field with the left mouse button several times from right to left, the "Need Help" modal window disappears
| Expected result | Characters entered in the Question field are highlighted with the left mouse button from right to left and the "Need Help" modal window does not disappear
| Attachments | https://drive.google.com/file/d/1D_FmhrsmfkonsyPwAUYF9fGwT3ixLihi/view?usp=sharing
Bug tracking | Severity | Minor
| Priority | Medium
Notes | Notes | The modal window disappears only when you select from right to left.

## Bug_10
Category | Label | Value
Bug overview | ID number | 10 | Fixed
| Reporter | Mykhailo Loshch
| Summary | On clicking the «Send» button in the «Need Help» PopUp, the «Email» field is validated without a dot in the name part
Environment | Deviсe | PC
| Operating system | Windows 11 Pro 22H2 22621.1848 X64
| Browser | Google Chrome Version114.0.5735.134 (Oficial Build), (64 bit)
Bug details | Preconditions | The Web App is opened in Browser
The user is logged in.
| Steps to reproduce | Click on the «Need Help» link on the SideBar
Enter to the «Need Help» PopUp RobiN@emailcom or similar
Click on the «Send» button
| Actual result | On clicking the «Send» button in the «Need Help» PopUp with entered data RobiN@emailcom at the «Email» field, the fields are validated and the request is sent to the backend, and the validation error message does not appear
| Expected result | On clicking the «Send» button in the «Need Help» PopUp with entered data RobiN@emailcom at the «Email» field, fields validation should not occur, and a validation error PopUp should appear
| Attachments | https://drive.google.com/file/d/1nOu_K3fwV1NKDsRqEPusUNcecwQu--1d/view?usp=sharing
Bug tracking | Severity | Minor
| Priority | Low
Notes | Notes

## Bug_11
Category | Label | Value
Bug overview | ID number | 11 | Fixed
| Reporter | Mykhailo Loshch
| Summary | On clicking the "Send" button in the "Need Help" PopUp, the validation of the "Email" field is not required and the validation error message does not appear
Environment | Deviсe | PC
| Operating system | Windows 11 Pro 22H2 22621.1848 X64
| Browser | Google Chrome Version114.0.5735.134 (Oficial Build), (64 bit)
Bug details | Preconditions | The Web App is opened in Browser
The user is logged in.
| Steps to reproduce | Click on the "Need Help" link on the SideBar.
Leave the "Email" field empty on the "Need Help" PopUp
Click on the "Send" button
| Actual result | On clicking the "Send" button in the "Need Help" PopUp without data in the "Email" field, the fields are validated and the validation error message does not appear
| Expected result | On clicking the "Send" button in the "Need Help" PopUp without data in the "Email" field, the fields are not validated and the validation error message appears
| Attachments | https://drive.google.com/file/d/1y9ZLxXLOVBfyHi8hNlblZirAm2rAlme9/view?usp=sharing
Bug tracking | Severity | Major
| Priority | Low
Notes | Notes

## Bug_12
Category | Label | Value
Bug overview | ID number | 12 | Fixed
| Reporter | Mykhailo Loshch
| Summary | On clicking the "Send" button in the "Need Help" PopUp, the validation of the "Question" field is not required and the validation error message does not appear
Environment | Deviсe | PC
| Operating system | Windows 11 Pro 22H2 22621.1848 X64
| Browser | Google Chrome Version114.0.5735.134 (Oficial Build), (64 bit)
Bug details | Preconditions | The Web App is opened in Browser
The user is logged in.
| Steps to reproduce | Click on the "Need Help" link on the SideBar.
| Actual result | Leave the "Question" field empty on the "Need Help" PopUp
Click on the "Send" button
On clicking the "Send" button in the "Need Help" PopUp without data in the "Question" field, the fields are validated and the validation error message does not appear
| Expected result | On clicking the "Send" button in the "Need Help" PopUp without data in the "Question" field, the fields are not validated and the validation error message appears
| Attachments | https://drive.google.com/file/d/1Oj35n7JqKyH0VlgBcaBgPNy6rHXhD_-h/view?usp=sharing
Bug tracking | Severity | Minor
| Priority | Low
Notes | Notes

## Bug_19
Category | Label | Value
Bug overview | ID number | 19 | Fixed
| Reporter | Mykhailo Loshch
| Summary | The "Title" field in the "Create a new board" pop-up window is validated when Cyrillic characters are entered.
Environment | Deviсe | PC
| Operating system | Windows 11 Pro 22H2 22621.1848 X64
| Browser | Google Chrome Version114.0.5735.134 (Oficial Build), (64 bit)
Bug details | Preconditions | The Web App is opened in Browser
The user is logged in.
| Steps to reproduce | 1. Click on the "Create a new board" button in the SideBar panel.
2. Enter Cyrillic characters in the "Title" field.
| Actual result | The "Title" field accepts Cyrillic characters.
| Expected result | When entering Cyrillic, a Pop Up with a validation error should appear.
| Attachments | https://drive.google.com/file/d/1Ra5POUaV5o_Vq5JUUdYNRt2C4dCgqeyF/view?usp=sharing
Bug tracking | Severity | Minor
| Priority | Low
Notes | Notes

## Bug_20
Category | Label | Value
Bug overview | ID number | 20 | Fixed
| Reporter | Mykhailo Loshch
| Summary | When saving a board with a name longer than 30 characters, the "Edit board" and "Delete board" icons are not visible in the list of boards on the Sidebar.
Environment | Deviсe | PC
| Operating system | Windows 11 Pro 22H2 22621.1848 X64
| Browser | Google Chrome Version114.0.5735.134 (Oficial Build), (64 bit)
Bug details | Preconditions | The Web App is opened in Browser
The user is logged in.
| Steps to reproduce | 1. Click the "Create a new board" button on the SideBar panel.
2. Enter more than 30 characters in the "Title" field
3. Click the "Create" button
4. Find the created board in the list of boards on the sidebar and try to click on the "Edit board" or "Delete board" icons.
| Actual result | On the created board, the "Edit board" or "Delete board" icons are not visible in the list of boards.
| Expected result | On the created board, the "Edit board" or "Delete board" icons are visible in the list of boards
| Attachments | https://drive.google.com/file/d/14MDYvILv79PkhoqXj2rZru6e6nxIzT7f/view?usp=sharing
Bug tracking | Severity | Minor
| Priority | Low
Notes | Notes | To see the "Edit board" and "Delete board" icons, you need to click on the name of the created board and click the right arrow on the keyboard until the icons appear!

## Bug_21
Category | Label | Value
Bug overview | ID number | 21 | Fixed
| Reporter | Mykhailo Loshch
| Summary | When changing the background of the board to the first "no background" icon in the "Edit board" Pop Up, the application freezes and the screen turns white.
Environment | Deviсe | PC
| Operating system | Windows 11 Pro 22H2 22621.1848 X64
| Browser | Google Chrome Version114.0.5735.134 (Oficial Build), (64 bit)
Bug details | Preconditions | The Web App is opened in Browser
The user is logged in.
| Steps to reproduce | 1. Click the "Edit board" button on the SideBar panel.
2. Enter a valid title in the "Title" field
3. Select the first background icon "without background"
4. Click the "Edit" button
| Actual result | After changing the background of the board to the first "no background" icon in the "Edit board" Pop Up, the application freezes and the screen turns white.
| Expected result | After changing the background of the board to the first "no background" icon in the Pop Up "Edit board", the background of the board changes.
| Attachments | https://drive.google.com/file/d/1lURteQcPuW6jBreuiiLcQo0HBKdykI8F/view?usp=sharing
Bug tracking | Severity | Minor
| Priority | Low
Notes | Notes

## Bug_22
Category | Label | Value
Bug overview | ID number | 22 | Fixed
| Reporter | Mykhailo Loshch
| Summary | When editing the "Title" field in the Pop Up "Edit board", the changes in the "Title" field are not saved.
Environment | Deviсe | PC
| Operating system | Windows 11 Pro 22H2 22621.1848 X64
| Browser | Google Chrome Version114.0.5735.134 (Oficial Build), (64 bit)
Bug details | Preconditions | The Web App is opened in Browser
The user is logged in.
| Steps to reproduce | 1. Click the "Edit board" button on the SideBar panel.
2. Enter a valid title in the "Title" field.
3. Click the "Edit" button.
| Actual result | After editing the "Title" field in the "Edit board" Pop Up, the changes in the "Title" field are not saved.
| Expected result | After editing the "Title" field in the Pop Up "Edit board", the changes in the "Title" field are saved.
| Attachments | https://drive.google.com/file/d/1kLUmDBpmdr8AdovUtl9y7h00Wdu3ynU4/view?usp=sharing
Bug tracking | Severity | Minor
| Priority | Low
Notes | Notes | For bugs 22,23, the "Title" field and Board icon change only together with the background, except for white.
https://drive.google.com/file/d/1W7YyHboN0X9UdPNT3peHoGM23kr6AyA6/view?usp=sharing

## Bug_23
Category | Label | Value
Bug overview | ID number | 23 | Fixed
| Reporter | Mykhailo Loshch
| Summary | When editing the board icon in the "Edit board" Pop Up, the new icon is not saved.
Environment | Deviсe | PC
| Operating system | Windows 11 Pro 22H2 22621.1848 X64
| Browser | Google Chrome Version114.0.5735.134 (Oficial Build), (64 bit)
Bug details | Preconditions | The Web App is opened in Browser
The user is logged in.
| Steps to reproduce | 1. Click the "Edit board" button on the SideBar panel.
2. Select any other board icon.
3. Click the "Edit" button.
| Actual result | After editing the board icon in the "Edit board" Pop Up, the new icon is not saved.
| Expected result | After editing the board icon in the "Edit board" Pop Up, the new icon is saved.
| Attachments | https://drive.google.com/file/d/1XOx4IyJx3baJphW_Bk2aSwx2WEaaS5a6/view?usp=sharing
Bug tracking | Severity | Minor
| Priority | Low
Notes | Notes